## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set up JDK 21, IntelliJ IDEA, and MySQL Workbench environment | MUST HAVE | No Dependency | Shubham | 3- Completed
S1 | S1 | US-002 | Define core data models: Account, Transaction, and custom exceptions | MUST HAVE | No Dependency | Shubham | 3- Completed
S1 | S1 | US-003 | Create database schema: users, accounts, and transactions tables | MUST HAVE | No Dependency | Shubham | 3- Completed
S2 | S2 | US-004 | Implement AccountService to create accounts (hashing passwords) | MUST HAVE | US-003 | Shubham | 3- Completed
S2 | S2 | US-005 | Implement login/logout flow for customers and admin | MUST HAVE | US-004 | Shubham | 3- Completed
S2 | S2 | US-006 | Add validation: Prevent duplicate emails | MUST HAVE | US-004 | Shubham | 3- Completed
S3 | S3 | US-007 | Implement TransactionService: Deposit, Withdraw (Atomic operations) | MUST HAVE | US-005 | Shubham | 3- Completed
S3 | S3 | US-008 | Log all transactions to MySQL (TransactionLogger) | MUST HAVE | US-007 | Shubham | 3- Completed
S3 | S3 | US-009 | Generate TXT reports in 'reports' folder | MUST HAVE | US-008 | Shubham | 3- Completed
S3 | S3 | US-010 | Implement Smart Transfer UI: Show list of other accounts | SHOULD HAVE | US-005 | Shubham | 3- Completed
S4 | S4 | US-011 | Implement AlertService: Email alert if balance < $100 | MUST HAVE | US-005, US-009 | Shubham | 3- Completed
S4 | S4 | US-012 | View all users, accounts, and transactions | SHOULD HAVE | US-005 | Shubham | 3- Completed
S4 | S4 | US-013 | Add logging (java.util.logging) for all user actions | MUST HAVE | No Dependency | Shubham | 3- Completed
S4 | S4 | US-014 | End-to-End Testing: Create -> Transact -> Report -> Email | MUST HAVE | All previous stories | Shubham | 3- Completed
S4 | S4 | US-015 | Generate PDF Statements with 'Digi Bank' branding | SHOULD HAVE | US-009 | Shubham | 3- Completed
S4 | S4 | US-016 | Prepare README.md, .gitignore, and LICENSE for GitHub submission. | MUST HAVE | No Dependency | Shubham | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7